## Investment guides
Proposed Target Timeline | Target Timeline | Activity Type | Topic | Data | Coffee |  | Cacao
[5 empty] | Institution | Point Person (Expertise) | Institution | Point Person (Expertise)
Q1, Q2 | To be determined | Ex-ante assessment of climate risks for value-chains | Assessing Climate Risks for Commodity Value Chain | Crop occurrence points for high harvested area except for Davao del Sur (for coffee and cacao) Iloilo and Bukidnon (for coffee) | PAGASA LGUs except Davao del Sur and Bukidnon UPLB-CFNR UPMin Nestle DA-RFOs/PRDP DA-PCAF DTI Catholic Relief Services (CRS) DENR-NGP Coffee for Peace | UPLB - Jun Tiburan and Nel Bantayan (GIS) UPMin - Dr. Acosta/ Nilo Oponda (GIS, Crop Suitability, LiDAR) Nestle PH - Art (Vice Pres for Prod) / Angel Wassner CRS - Chin Nobleza PAGASA - Flaviana Hilario / Edna Juanillo | PAGASA LGUs except Davao del Sur UPLB-CFNR UPMin Kennemer/Mars DA-RFOs/PRDP DA-PCAF DTI Catholic Relief Services (CRS) DENR-NGP CIDAMI Cordero Farm (Koronadal) Malagos Gardens (Davao) Options Inc. (group of traders and producers of cacao) | UPLB - Jun Tiburan / Nel Bantayan (GIS) UPMin - Dr. Acosta / Nilo Oponda (GIS, Crop Suitability, LiDAR) Kennemer - CRS - Chin Nobleza PAGASA - Flaviana Hilario / Edna Juanillo Options, Inc. - Josephine Ramos
Q2, Q3 | To be determined | Chain-wide consultation for cope-adjust-transform analysis | Determing wide chain adapatation and mitigation options | Portfolio of CRA Practices | PAGASA LGUs except Davao del Sur and Bukidnon UPLB-CFNR UPMin Nestle DA-RFOs/PRDP DA-PCAF DTI Catholic Relief Services (CRS) Coffee for Peace + farmer groups, coffee board, traders, processors, PSA | PAGASA - Edna L. Juanillo/ Flaviana Hilario UPLB - Dr. Jun Tiburan and Dr. Nel Bantayan (GIS) UPMin - Dr. Acosta/ Dr. Nilo Oponda (Vice Chancellor) [GIS, Crop Suitability, LiDAR] Nestle PH- (Vice Pres for Prod) Art (Makati Office) Angel Wassner (main office) CRS - Ms. Chin Nobleza (Program Manager) | PAGASA LGUs except Davao del Sur UPLB-CFNR UPMin Kennemer/Mars DA-RFOs/PRDP DA-PCAF DTI Catholic Relief Services (CRS) DENR-NGP CIDAMI Cordero Farm (Koronadal) Malagos Gardens (Davao) Options Inc. (group of traders and producers of cacao) | PAGASA - Edna L. Juanillo/ Flaviana Hilario UPLB - Dr. Jun Tiburan and Dr. Nel Bantayan (GIS) Kennemer - UPMin - Dr. Acosta/ Dr. Nilo Oponda (Vice Chancellor) [GIS, Crop Suitability, LiDAR] CRS - Ms. Chin Nobleza (Program Manager) Options, Inc. - Josephine Ramos
Q2, Q3 | To be determined | Carbon stock and carbon footprint assessment of adaptation options |  | Diameter Volume Height Biomass (plot sampling) Allometric measure (if available) Tissue analysis Carbon content analysis | UPLB-CFNR UPMin | UPLB-CFNR - Fulgencia Pulhin / Ana Codilan UPMin - | UPLB-CFNR UPMin | UPLB-CFNR - Fulgencia Pulhin / Ana Codilan UPMin -
Q3 | To be determined | Cost-benefit and trade-off analysis of adaptation options which have high mitigation potential |  | Depends on the portfolio of CRA Practices: plantation vs. intercropping (dominant farming system) Different market outlets (Nestle, traders, coops/producer orgs) Time series data (price, volume, costs, rainfall) Yield data Cost data (labor and material inputs) By variety (including slope) | UPLB-CFNR UPMindanao | UPLB-CFNR - Marge Calderon/ Canesio Predo/ Vanessa Palma UPMin - Larry Digal/ May Anne Mata | UPLB-CFNR UPMindanao | UPLB-CFNR - Marge Calderon/ Canesio Predo/ Vanessa Palma UPMin - Larry Digal/ May Anne Mata
Q3 | To be determined | Value-chain actors and stakeholder validation of results |  | Output from previous CBA from activities (C3-C6) | CIAT + institutions in F3 | To be determined | CIAT + institutions in F3 | To be determined
Q3, Q4 | To be determined | Developing portfolio of CRA options for coffee and cacao | Developing CRA investment guides for coffee and cocoa | Revised output from previous CBA (C3-C7) | IIRR UPMindanao UPLB-CFNR | IIRR - Rene Vidallo UPMin - Larry Digal / May Anne Mata UPLB-CFNR - Marge Calderon / Canesio Predo / Vanessa Palma | IIRR UPMindanao UPLB-CFNR | IIRR - Rene Vidallo UPMin - Larry Digal / May Anne Mata UPLB-CFNR - Marge Calderon / Canesio Predo / Vanessa Palma
Q4 | To be determined | Value-chain actors and stakeholders’ consultation on proposed CRA portfolios |  | Output from C8 | CIAT + institutions in F3 | To be determined | CIAT + institutions in F3 | To be determined
Q4 | To be determined | Formulating CRA investment plans for value chain actors |  | Output of C9 to formulate the investment plans | CIAT + institutions in F3 | To be determined | CIAT + institutions in F3 | To be determined
Q4 | To be determined | Preparing CRA investment guides |  | Output of C10 as basis for preparing the CRA investment guides | IIRR UPMindanao UPLB-CFNR | IIRR - Rene Vidallo UPMin - Larry Digal / May Anne Mata UPLB-CFNR - Marge Calderon / Canesio Predo / Vanessa Palma | IIRR UPMindanao UPLB-CFNR | IIRR - Rene Vidallo UPMin - Larry Digal / May Anne Mata UPLB-CFNR - Marge Calderon / Canesio Predo / Vanessa Palma
Q4 | To be determined | Launching and sharing of investment guides |  | Investment plans, documentations | CIAT + institutions in F3 | To be determined | CIAT + institutions in F3 | To be determined
Q4 | To be determined | Project completion and results dissemination meeting |  | Final reports, deliverables | CIAT + institutions in F3 | To be determined | CIAT + institutions in F3 | To be determined
* Q1- 1st Quarter of the year
* Q2- 2nd Quarter of the year
* Q3- 3rd Quarter of the year
* Q4- 4th Quarter of the year
Note on E3: Dikitanan, Rowell: Province with high harvested area Cacao: Compostela Valley, Davao del Norte, Davao del Sur Davao Oriental, Agusan del Sur Coffee: Sultan Kudarat, Bukidnon, Cavite, Iloilo, Davao del Sur